#### KUMASI METROPOLITAN ASSEMBLY

#### 2026 ANNUAL ACTION PLAN

| Objective: 1.3.1 Enhance business enabling environment |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme : Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Update data on Businesses in Kumasi | Metro Wide |  |  |  |  | 20,000 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| Organize a business forum to enhance public and private sector synergies |  |  |  |  |  | 10,000 | 20,000 |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| Facilitate and support formalization of informal SMEs | Metro Wide |  |  |  |  | 1,000 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| Organize training on on-line sales for SMEs | Metro Wide |  |  |  |  | 10,000 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| Develop comprehensive LED strategy | Metro Wide |  |  |  |  | 4,000 | 16,000 |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| Objective: 1.5.1 Diversify and expand the tourism industry |  |  |  |  |  |  |  |  |  |  |  |  |
| Organize quarterly radio-talk show on the potentials of local tourism | Metro Wide |  |  |  |  | 4000 | 4000 |  |  |  | Trade & Investment | GTA |
| Institute and organise annual home coming carnival | Metro Wide |  |  |  |  | 10,000 | 40,000 |  |  |  | Trade & Investment committee | GTA |
| Objective: 1.6.2 Enhance agricultural production and agri-business for economic transformation |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct home and farm visits to advice farmers (40% females and 60% males) and organize weekly market price surveys. | Metro Wide |  |  |  |  |  | 5,500 |  |  |  | Agric Dept | Market Queens |
| 4 MOAs to visit AEAs under their supervision to guide and offer technical backstopping. | Metro Wide |  |  |  |  |  | 5,000 |  |  |  | Agric Dept | Beneficiaries |
| Conduct two monitoring visits to all field projects ( MCE and Director of Agric) | Metro Wide |  |  |  |  | 6,000 |  |  |  |  | Agric Dept | Beneficiaries |
| Organize 4 trainings on urban CSA practices and Train 100 women in rice branding and quality packaging tech | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | Agric Dept | Beneficiaries |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Organise training on GAPS and climate Smart practices | Metro Wide |  |  |  |  |  | 5,000 |  |  |  | Agric Dept | Beneficiaries |
| Train rice processors on branding and standardization and Conduct Fruit Juice Processing for Fruit Vendors | Metro Wide |  |  |  |  | 7,000 |  |  |  |  | Agric Dept | Beneficiaries |
| Organize Farmers Day celebration | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | Agric Dept | Beneficiaries |
| Train 150 households on soya fortification & local food processing | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | Agric Dept | Beneficiaries |
| Renovate Metro Agric Office | MOFA |  |  |  |  |  | 500,000 |  |  |  | Agric Dept | Works Dept. |
| Train livestock farmers on meat handling & processing and cold-store operators on food preservation, Storage & hygiene | Metro Wide |  |  |  |  |  | 8,500 |  |  |  | Agric Dept | Environmental Health |
| Weekly disease surveillance on: Avian Influenza, Rabies, Pest de Petit Ruminal and CBPP | Metro Wide |  |  |  |  | 6,000 |  |  |  |  | Agric Dept | Works Dept. |
| Organize one training session for 30 women in 4 basic schools undertaking school feeding program | MOFA Office |  |  |  |  | 4,000 |  |  |  |  | Agric Dept | Works Dept. |
| Organise four plant clinics for women farmers at four different operational areas. | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | Agric Dept | Works Dept. |
| Organize monthly technical review meetings for 25 staff (6 females and 21 males). | MOFA Office |  |  |  |  | 6,000 |  |  |  |  | Agric Dept | Works Dept. |
| Train 24H Market Pilot traders on night market food handling, safety & lighting | MOFA Office |  |  |  |  | 6,000 |  |  |  |  | Agric Dept | Works Dept. |
| Organize training for 20 women vegetable traders on grading, standardization and packaging | Bantama and Abinkyi |  |  |  |  |  | 3000 |  |  |  | Agric Dept | Market women |
| Train 200 women on Post Harvest Losses in 4 Markets | Metro Wide |  |  |  |  |  | 5,000 |  |  |  | Agric Dept | Market women |
| Rehabilitate 1No. Market and Construct 24Hour Economy Market | Race Course Krofofrom |  |  |  |  |  | 9,000,000 |  |  |  | Agric Dept | Works Dept Market women |
| Objective: 2.1.1 Improve coordination of population governance |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Social Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Objective: 2.1.1 Improve coordination of population governance (Birth and Death) |  |  |  |  |  |  |  |  |  |  |  |  |
| Organize Mobile and mob up registration of Birth and Death | Atasomanso, Sepe, Dichemso, Kejetia |  |  |  |  |  | 4500 |  |  |  | Birth and Death | Beneficiaries |
| Organize Birth and Deaths Week Celebration | Ahodwo, Sokoban, Adiebeba |  |  |  |  |  | 5000 |  |  |  | Birth and Death | Beneficiaries |
| Objective: 2.3.7 Provide adequate health infrastructure and institute functional health logistics (Health) |  |  |  |  |  |  |  |  |  |  |  |  |
| Rehabilitate and furnish Moshie Zongo Health Centre | Moshie Zongo |  |  |  |  | 1,500,000 | 2,700,00 |  |  |  | Health | Works |
| Construct Pedeatric Centre at KMA Clinic (CHPS Compound) | Adum |  |  |  |  |  | 3,000,000 |  |  |  | Health | Works |
| Objective: 2.3.8 Strengthen healthcare and health service delivery management system (Health) |  |  |  |  |  |  |  |  |  |  |  |  |
| Support NID/ malarial control programme | Metro Wide |  |  |  |  |  | 4000 |  |  |  | Health | Beneficiaries |
| Support cancer prevention programme (C- CAN) | Metro Wide |  |  |  |  |  | 4000 |  |  |  | Health | Beneficiaries |
| Introduce and promote telemedicine to improve health care services | Metro Wide |  |  |  |  | 3,000 |  |  |  |  | Health | Beneficiaries |
| Organize HIV/AIDS awareness program | Metro Wide |  |  |  |  |  | 150,000 |  |  |  | Health | Beneficiaries |
| Organize one meeting annually between the Assembly and private health Operators for effective Health service delivery | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | Health | Beneficiaries |
| Organize stake holder meetings on safe motherhood and on appropriate nutrition -Iron folic supplementation | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | Health | Beneficiaries |
| Screen OPD patients for HBP and organize annual education on healthy lifestyle | Metro Wide |  |  |  |  |  | 4,500 |  |  |  | Health | Beneficiaries |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Objective: 2.3.7 Provide adequate health infrastructure and institute functional health logistics (Health) |  |  |  |  |  |  |  |  |  |  |  |  |
| Rehabilitate and furnish Moshie Zongo Health Centre | Moshie Zongo |  |  |  |  | 1,500,000 | 2,700,00 |  |  |  | Health | Works |
| Construct Pedeatric Centre at KMA Clinic (CHPS Compound) | Adum |  |  |  |  |  | 3,000,000 |  |  |  | Health | Works |
| Objective: 2.3.8 Strengthen healthcare and health service delivery management system (Health) |  |  |  |  |  |  |  |  |  |  |  |  |
| Support NID/ malarial control programme | Metro Wide |  |  |  |  |  | 4000 |  |  |  | Health | Beneficiaries |
| Support cancer prevention programme (C- CAN) | Metro Wide |  |  |  |  |  | 4000 |  |  |  | Health | Beneficiaries |
| Introduce and promote telemedicine to improve health care services | Metro Wide |  |  |  |  | 3,000 |  |  |  |  | Health | Beneficiaries |
| Organize HIV/AIDS awareness program | Metro Wide |  |  |  |  |  | 150,000 |  |  |  | Health | Beneficiaries |
| Organize one meeting annually between the Assembly and private health Operators for effective Health service delivery | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | Health | Beneficiaries |
| Organize stake holder meetings on safe motherhood and on appropriate nutrition -Iron folic supplementation | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | Health | Beneficiaries |
| Screen OPD patients for HBP and organize annual education on healthy lifestyle | Metro Wide |  |  |  |  |  | 4,500 |  |  |  | Health | Beneficiaries |
| Train more staff to test and treat TB cases 14 | MHD |  |  |  |  |  | 5000 |  |  |  | Health | Beneficiaries |
| Strengthen surveillance and supervise facilities to ensure that emergency protocols are followed | Metro Wide |  |  |  |  | 2000 |  |  |  |  | Health | Beneficiaries |
| Integrate supportive supervision in health facilities in Kumasi | Metro Wide |  |  |  |  |  | 50,000 |  |  |  | Health | Network of Practice |
| Train health staff on prevention and management of non-communicable diseases | Metro Health Directorate |  |  |  |  |  |  | 120,000 |  |  | Health | Medtronic LABS |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Objective: 2.5.1 Improve access to safe, reliable and sustainable water supply services for all (Water) |  |  |  |  |  |  |  |  |  |  |  |  |
| Construct 10No. Mechanized Boreholes and repair and maintain 5No. (Metro Wide) | Metro Wide |  |  |  |  |  | 700,000 |  |  |  | Works | Beneficiaries |
| Objective: 2.5.2 Enhance access to improved and sustainable environmental sanitation services (Waste Management and Environment) |  |  |  |  |  |  |  |  |  |  |  |  |
| Construct 5No. Skip Pads & supply 5No. 14 Containers | Metro Wide |  |  |  |  |  | 650,000 |  |  |  | WMD | EHU |
| Procure and distribute waste collection containers, PPEs, sanitary tools and motorized tricycles. | Metro Wide |  |  |  |  |  | 300,000 |  |  |  | WMD | EHU |
| Roll out a prog to promote waste segregation at source & sorting in selected communities and schools | Metro Wide |  |  |  |  | 3,000 |  |  |  |  | WMD | EHOs |
| Implement Sanitation Improvement Package (SIP) and Fumigation | Metro Wide |  |  |  |  |  | 1,200.000 |  |  |  | WMD | Zoomlion |
| Assess service providers capacities and monitor their operations | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | WMD | SP |
| Monitor the operations of waste treatment and disposal facilities and Heavy-Duty Equipment | Oti |  |  |  |  |  | 500,000 |  |  |  | WMD | JSO |
| Construction of Re-enforced Concrete Head Wall | Oti |  |  |  |  | 350000 |  |  |  |  | WMD | EHU |
| Review of the Contract for street sweeping, drainage cleansing and any other waste management contract | Main Admin |  |  |  |  |  | 20,000 |  |  |  | WMD | EHU |
| Support/Sustain the implementation of the Central Market/CBD night cleaning and Litter Control program | Metro Wide |  |  |  |  |  | 1,200,000 |  |  |  | WMD | EHU |
| Build the capacity of EHOS/ Waste Management staff for effective sanitation service delivery | Main Admin |  |  |  |  |  | 10,000 |  |  |  | WMD | HR |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Issue Abatement notice to homeowners without toilet facilities and facilitate the Const. of 100no. HH Toilets in low income HHs | Metro Wide |  |  |  |  |  | 5,000 |  |  |  | WMD | EHOs |
| Organize 20 Community Durbars and 20 clean up campaigns | Metro Wide |  |  |  |  | 50,000 |  |  |  |  | WMD | EHOs |
| Organize quarterly inspection at all transfer stations and public toilets at sub-metro level | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | WMD | EHOs |
| Organize food hygiene education for school feeding caterers and conduct routine food handler screening and certification | Metro Wide |  |  |  |  | 30,000 |  |  |  |  | WMD | EHU |
| Intensify premises inspection and environmental Health Sanitation prosecutions | Metro Wide |  |  |  |  | 5000 |  |  |  |  | WMD | EHU |
| Objective: 2.5.3 Promote efficient and sustainable waste management (Waste Management) |  |  |  |  |  |  |  |  |  |  |  |  |
| Support for the Rehabilitation and expansion of 2No. Sewage Ponds | Asafo Adum |  |  |  |  | 50,000 |  |  |  |  | WMD | Works |
| Objective: 2.6.1 Enhance equitable access to, and participation in quality education at all levels (Education) |  |  |  |  |  |  |  |  |  |  |  |  |
| Construct 2No. Classroom Blocks | Santaasi M/A Adumanu Phase II |  |  |  |  | 1,500,000 |  |  |  |  | Education | Works |
| Rehabilitate 7N0. Classroom Blocks and Construct 1No. KG | Asem Opoku Ware Basic |  |  |  |  |  | 1,600.000 |  |  |  | Education | Works |
| Construct 3No. 6Unit Classroom Blocks | Adabiya Islamic Adiebeba M/A Armed Forces Basic |  |  |  |  |  | 3,000,000 |  |  |  | Education | Works |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Procure 7000 school furniture for schools | Metro Wide |  |  |  |  |  | 3,200.000 |  |  |  | Education | Beneficiaries |
| Provide Sponsorship for 200 (120 girls and 80 boys) needy but brilliant students | Metro Wide |  |  |  |  |  | 150,000 |  |  |  | Education | Heaachers |
| Organize Mock Exams for pupils in JHS in the Kumasi Metropolis | Metro Wide |  |  |  |  | 10,000 | 25,000 |  |  |  | Education |  |
| Organize reading festival to promote early grade reading | Asem/ |  |  |  |  | 2,000 | 33000 |  |  |  | Education | Beneficiaries |
| Support the organization of my First Day and National Day celebrations | Metro Wide |  |  |  |  | 10,000 | 150,000 |  |  |  | Education | Beneficiaries |
| Support the organization of Metro Best Teachers’, Worker and School Award | Metro Wide |  |  |  |  | 45000 |  |  |  |  | Education | Beneficiaries |
| Support the organization of STMIE Clinic for girls to promote Science, Mathematics and Tech | Metro Wide |  |  |  |  | 47500 |  |  |  |  | Education | Beneficiaries |
| Objective: 2.9.3 Strengthen social protection for the vulnerable (Social Welfare) |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect GPS data on needy, vulnerable and marginalized and provide them with support | Metro Wide |  |  |  |  | 4000 | 2000 |  |  |  | SW&CD | Beneficiaries |
| Organize programmes for 60 PWDs and their dependents and link them up to NHIS | Metro Wide |  |  |  |  | 3,500 | 7,500 |  |  |  | SW&CD | Beneficiaries |
| Organize educational program for children on rights and responsibilities | Metro Wide |  |  |  |  | 5,000 | 1,000 |  |  |  | SW&CD | Beneficiaries |
| Carry out LEAP activities to benefit 3150 beneficiaries, through home visits and referral | Metro Wide |  |  |  |  | 2,000 | 80,000 |  |  |  | SW&CD | Beneficiaries |
| Render personal welfare services to 40 indigents and link them up to NHIS and other social intervention | Metro Wide |  |  |  |  |  | 6,000 |  |  |  | SW&CD | Beneficiaries |
| Provide hospital welfare services to 30 patients | Metro Wide |  |  |  |  |  | 7,000 |  |  |  | SW&CD |  |
| Reunite children in residential homes with their families and relations | Metro Wide |  |  |  |  | 3,000 | 3000 |  |  |  | SW&CD | Beneficiaries |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Educate 20 teenage Head Porters (Kayaye) leaders on personal care, health, rights and others | Metro Wide |  |  |  |  | 3,000.00 | 1,500 |  |  |  | SW&CD |  |
| Undertake case mangt to strengthen Families for the benefit 60 children/clients | Metro Wide |  |  |  |  | 5000 | 15,000.00 |  |  |  | SW&CD |  |
| Organize talk sessions on child abuse, time mangt, labor and molestation for students | Metro Wide |  |  |  |  | 3000 | 3000 |  |  |  | SW&CD | Beneficiaries |
| Monitor, register and renew certificates and organize training for 30 day centers and 30 NPOs/NGOs | Metro Wide |  |  |  |  | 4000 | 2000 |  |  |  | SW&CD |  |
| Support 100 PWDs in the Metropolis | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | SW&CD | Beneficiaries |
| Objective: 2.10.1 Attain gender equality and equity in political and social development (Gender) |  |  |  |  |  |  |  |  |  |  |  |  |
| Sensitize 3 women groups on Gender Based Violence and its preventive measures | Metro Wide |  |  |  |  | 5000 |  |  |  |  | SW&CD |  |
| Organize activities to celebrate Breast Cancer Awareness Month | Metro Wide |  |  |  |  | 10,000 | 20000 |  |  |  | GDO | Beneficiaries |
| Objective: 3.5.1 Reduce Environmental Pollution |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Environment and Human Settlement Development (Environment) |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Calibrate noise emitting devices of new 120 institutions and carry out 12 radio educational programmes on noise pollution and the environment | Metro Wide |  |  |  |  | 20,000 |  |  |  |  | WMD |  |
| Objective: 3.7.2 Enhance climate change resilience (Forestry) |  |  |  |  |  |  |  |  |  |  |  |  |
| Plant and Nurture to growth 5,000 trees in schools, communities and along major routes | Metro Wide |  |  |  |  |  | 20000 |  |  |  | Forestry | Environmental Health Unit |
| Implement Bloomberg sponsored Youth Climate Action project | Metro wide |  |  |  |  |  |  | 1,000,000 |  |  | MPCU |  |
| Organize sensitization exercises in communities on the need to plant more trees | Metro Wide |  |  |  |  |  | 10000 |  |  |  | Forestry | Environmental Health Unit |
| Objective: 3.8.1 Improve efficiency and effectiveness of road transport infrastructure and services (Urban Roads) |  |  |  |  |  |  |  |  |  |  |  |  |
| Construct 5No. Metal footbridges | Metro Wide |  |  |  |  |  | 500,000 |  |  |  | Metro Roads | Assembly Members |
| Maintenance of Metal Footbridges | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | Metro Roads | Assembly Members |
| Construct Drains in 3No. areas and improve box culvert and access roads | Abrepo Junc. Krofrom E FNT/ Truba |  |  |  |  |  | 1,000,000 |  |  |  | Metro Roads | Assembly Members |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Install Pedestrian Guardrails and replace metal gratings and slaps | GRA Area KATH |  |  |  |  |  | 100,000 |  |  |  | Metro Roads | Assembly Members |
| Maintenance of Green area and Grasscutting works at the medians | Suame R/A-Sofoline; Ahmadiya R/A-Asafo Neoplan; Ahmadiya R/A-Consar, Nhyiaeso, Ridge & Danyame areas |  |  |  |  |  | 100,000 |  |  |  | Metro Roads |  |
| Regrading of selected roads in the Kumasi Metropolis | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | Metro Roads | Hon. Assembly Members |
| Objective: 3.8.2 Enhance safety and security for all categories of road users |  |  |  |  |  |  |  |  |  |  |  |  |
| Carry out operational activities to improve upon public transport services &urban mobility | Metro Wide |  |  |  |  | 20000 |  |  |  |  | Transport Dept. | MTTD |
| Implement the KMA/Ibes Smart Transport Systems projects | Metro Wide |  |  |  |  | 15,000 | 20,000 |  |  |  | Transport Dept. |  |
| Implement the partnership for Healthy Cities Road Safety project/ BIGRS | Metro Wide |  |  |  |  |  | 30,000 |  |  |  | Transport Dept. | MTTD |
| Procure 2000 complete Street lights for the Kumasi Metropolis | Metro Wide |  |  |  |  |  | 1,000,000 |  |  |  | Works | Assembly Members |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Objective: 3.12.1 Promote sustainable spatially integrated development of human settlements (Physical Planning) |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify, verify and acquire lease on all lands zoned for public use across the metropolis (phase 1) | Metro Wide |  |  |  |  |  | 70,000 |  |  |  | Physical Planning | Traditional Authority |
| Organize 12 Statutory Technical and Spatial Planning Committee meetings | PPD |  |  |  |  | 264,000 |  |  |  |  | Physical Planning | HODs |
| Revise local plans, develop community maps/signages and procure street signages | Metro Wide |  |  |  |  | 1,000,000 |  |  |  |  | Physical Planning | Traditional Authority |
| Organize Planning Workshops and Greater Kumasi Comprehensive Urban Conference | Metro Wide |  |  |  |  | 70,000 |  |  |  |  | Physical Planning | HODs |
| Produce Ornamental plants and Maintain Town gardens | Metro Wide |  |  |  |  | 22,000 |  |  |  |  | Physical Planning | Urban Roads |
| Organize workshop on new land law for TSC/SPC and Assembly Members | PPD |  |  |  |  | 10,000 |  |  |  |  | Physical Planning | Assembly Members |
| Develop Hydrant and Lay – By/ Bus shelter Master Plan | Metro Wide |  |  |  |  | 70,000 |  |  |  |  | Physical Planning | GNFS/DUR |
| Organize sensitization campaigns to educate the public on building on unauthorized areas, on acquisition of land and permitting procedures | Metro Wide |  |  |  |  | 30,000 |  |  |  |  | Physical Planning | PRO |
| Organize periodic monitoring exercises to ensure Conformity to standards by developers | Metro Wide |  |  |  |  | 20,000 |  |  |  |  | Works | SPC |
| Procure working tools (Schmidt hammer, Wheel measuring roller) for effective supervision | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | Works | PPD |
| Objective: 3.14.1 Promote sustainable urban development |  |  |  |  |  |  |  |  |  |  |  |  |
| Organize educational campaigns on fire and floods for all fuel stations | Metro Wide |  |  |  |  | 8,000 | 3,000 |  |  |  | NADMO | Fire Service/ WMD |
| Carryout inspection and evaluation of facilities to ensure safety | Metro Wide |  |  |  |  |  | 10,000 |  |  |  | NADMO | Works |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Desilt chocked drains and streams | Metro Wide |  |  |  |  |  | 70,000 |  |  |  | NADMO | Works/Urban Roads |
| Build the Capacity of NADMO Staff in disaster management | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | NADMO | HR |
| Organize celebration of World Disaster Day | Metro Wide |  |  |  |  |  | 4000 |  |  |  | NADMO |  |
| Form Disaster Prevention groups in schools and communities | Metro Wide |  |  |  |  |  | 20,000 |  |  |  | NADMO | Assembly Members/Schools |
| Objective: 3.16.1 Promote effective maintenance culture |  |  |  |  |  |  |  |  |  |  |  |  |
| Plan and Budget for Maintenance of all Projects in the Kumasi Metropolis | Metro Wide |  |  |  |  |  | 1,000,000 |  |  |  | Central Admin | Works |
| Objective: 4.2.1 Deepen political and administrative decentralization |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: Governance and Institutional Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Organize 2no Town hall meetings annually to account community members on the implementation of Assembly programmes and activities | Prempeh Assembly Hall |  |  |  |  |  | 40,000 |  |  |  | Planning Unit | Budget & Ratings |
| Complete the construction of 2No. Sub metro Offices | Bantama Manhyia N |  |  |  |  | 1,000000 |  |  |  |  | Works | Beneficiaries |
| Support for Community Initiated projects and Sub District Structures | Metro Wide |  |  |  |  | 500000 |  |  |  |  | Central Admin | Assembly Members |
| Organize talk shows at radio stations to explain the services provided by the Assembly & how to access them | Metro Wide |  |  |  |  | 10,000 |  |  |  |  | PRO | ISD |
| Organize MCE’s electoral area tour | Metro Wide |  |  |  |  | 10,000 | 10,000 |  |  |  | PRO | ISD |
| Rehabilitate Office & residential buildings | Metro Wide |  |  |  |  |  | 500,000 |  |  |  | Works | HODs |
| Procure Office Supplies including computers, Laptops, Furniture, etc | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | IT Unit | Beneficiaries |
| Objective: 4.2.2 Improve decentralised planning |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare 2027 Annual Action Plan and Composite Budget and 2026 – 2029 MTDP | Metro Wide |  |  |  |  |  | 800,000 |  |  |  | MPCU | Assembly Members |
| Conduct routine monitoring and evaluation of Assembly’s projects and programs | Metro Wide |  |  |  |  |  | 200,000 |  |  |  | MPCU | Assembly Members |
| Organise quarterly MPCU/Budget Committee meetings | Metro Wide |  |  |  |  |  | 60,000 |  |  |  | MPCU | Budget Comm |
| Organize participatory M&E on assembly activities | Metro Wide |  |  |  |  |  | 70,000 |  |  |  | MPCU | Assembly Members |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Objective: 4.8.1 Enhance public safety and security |  |  |  |  |  |  |  |  |  |  |  |  |
| Organize radio talk shows on safety and crime prevention | Metro Wide |  |  |  |  |  | 10,000 |  |  |  | legal | Police |
| Support Security Services/City Guards to undertake effective community and law enforcement | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | legal | Police |
| Objective: 4.2.3 Strengthen fiscal decentralization |  |  |  |  |  |  |  |  |  |  |  |  |
| Train Staff of the Assembly on Performance Based Budgeting and GIFMIS | Metro Wide |  |  |  |  | 5000 | 5000 |  |  |  | Budget | Finance |
| Provide IT system to link centralized departments to the revenue unit | Metro Wide |  |  |  |  |  | 15,000 |  |  |  | IT | Finance |
| Organize radio programs monthly to educate tax payers about the need to pay taxes | Metro Wide |  |  |  |  | 5000 |  |  |  |  | Finance | PRO |
| Organize stakeholder engagements with the business community on Fee fixing resolution | Prempeh Assembly Hall |  |  |  |  | 5000 | 5000 |  |  |  | Budget | Finance |
| Review Budget/Plan at Mid- year and prepare revenue improvement action plan | Metro Wide |  |  |  |  | 3000 |  |  |  |  | Budget | Finance |
| Organize Budget implementation monitoring and training at the submetros | Metro Wide |  |  |  |  | 5000 |  |  |  |  | Budget | Finance |
| Train staff on Data Collection and Management & implement Smart Cities Project | Metro Wide |  |  |  |  |  | 500,000 |  |  |  | Central Admin | Budget & Ratings |
| Objective: 4.4.1 Strengthen the effectiveness, accountability, and efficiency of public institutions |  |  |  |  |  |  |  |  |  |  |  |  |
| Organize Training for Assembly Staff on the Local Government Service Protocol | Metro Wide |  |  |  |  |  | 30,000 |  |  |  | HR | HODs |
| Organize Training for Assembly staff on Communication skills | Metro Wide |  |  |  |  |  | 30,000 |  |  |  | HR | HODs |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Organize Training for Assembly Staff on electronic payment system and smart work place system | Metro Wide |  |  |  |  |  | 10,000 |  |  |  | HR | HODs |
| Organize Training for Assembly members on Negotiation and lobbying skills and Project Management | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | HR | HODs |
| Disseminate & organize stakeholder engagement on the 2021 Census and organize data collection on hotspots for drug peddlers especially the youth | Metro Wide |  |  |  |  |  | 15,000 |  |  |  | Statistics | PRO |
| Train MPCU Members on use of Stats Bank, Excel and Kobo Collect Tool | Metro Wide |  |  |  |  | 10,000 |  |  |  |  | Statistics |  |
| Objective: 5.2.2 Enhance Ghana’s international image and influence |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme: International Relations |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Location | 2026 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
|  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |
| Create two new International Partnerships and renew/revive three dormant partnerships | Metro Wide |  |  |  |  |  | 50,000 |  |  |  | Central Admin | Assembly Members HODs |
| Support the participation of Assembly Members and Staff of the Assembly in International Partnerships | Metro Wide |  |  |  |  |  | 300,000 |  |  |  | Central Admin | Assembly Members HODs |