#### **KUMASI METROPOLITAN ASSEMBLY**

#### **DRAFT 2022 ANNUAL ACTION PLAN**

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| **Development Dimension I – Economic Development** | | | | | | | | | | | | | | |
| 4. Economic Development | SP 4.1  Development of Trade and Industry | Form Local economic development Committee | Metro Wide |  |  |  |  | 2,500 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| 4. Economic Development | SP 4.1  Development of Trade and Industry | Update data on SMEs | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| 4. Economic Development | SP 4.1  Development of Trade and Industry | Organize a business forum to enhance public and private sector synergies |  |  |  |  |  | 5,000 | 20,000 |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| 4. Economic Development | SP 4.1  Development of Trade and Industry | Facilitate and support formalization of informal SMEs | Metro Wide |  |  |  |  | 1,000 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| 4. Economic Development | SP 4.1  Development of Trade and Industry | Organize training on on-line sales for SMEs | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| 4. Economic Development | SP 4.1  Development of Trade and Industry | Support artisans to manufacture machines and equipment for local manufacturing companies | Amakom/Asafo/Bantama/Santaase R/A |  |  |  |  |  |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 4. Economic Development | SP 4.1  Development of Trade and Industry | Facilitate the establishment of an Abattoir and feed production factories under the 1D1F Programme | Metro Wide |  |  |  |  | 2,000 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| 4. Economic Development | SP 4.1  Development of Trade and Industry | Develop comprehensive LED strategy | Metro Wide |  |  |  |  | 4,000 | 16,000 |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |
| 4. Economic Development | SP 4.2  Tourism Development | Organize quarterly radio-talk show on the potentials of local tourism | Metro Wide |  |  |  |  | 4000 | 4000 |  |  |  | Trade & Investment committee | GTA |
| 4. Economic Development | SP 4.2  Tourism Development | Institute and organise annual home coming carnival | Metro Wide |  |  |  |  | 10,000 | 40,000 |  |  |  | Trade & Investment committee | GTA |
| 4. Economic Development | SP 4.2  Tourism Development | Facilitate construction of museum | Adum |  |  |  |  | 5000 | 5000 |  |  |  | Trade & Investment committee | GTA |
| 4. Economic Development | SP 4.2  Tourism Development | Construct multi-purpose conference facility | Adum |  |  |  |  |  |  | PPP |  |  | Trade & Investment committee | Works |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 4. Economic Development | SP 4.1  Development of Trade & Industry | Construct 6No. Markets | Central Market, Krofrom, Bantama, Asafo, Amakom & Buokrom |  |  |  |  |  |  | PPP |  |  | Trade & Investment committee | Works |
| 4. Economic Development | SP 4.1  Development of Trade and Industry | Reconstruct 2No. Markets | Santaasi/ Kwadaso Estate |  |  |  |  |  |  | PPP |  |  | Trade & Investment committee | Works |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Organize regular engagements with traders at various markets | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | Trade & Investment committee | Market Queens |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Conduct (50) demonstrations on good agronomic practice on rice, maize and spring onions | Metro Wide |  |  |  |  |  | 5,000 |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Organize three hundred (300) field days on various crops (i.e.) maize, rice and spring onion on how to carry out good agronomic practices. | Metro Wide |  |  |  |  |  | 4,000 |  |  |  | Agric Dept | Beneficiaries |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Conduct home and farm visits. | Metro Wide |  |  |  |  |  | 4,000 |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Conduct twelve disease surveillance in the 4 operational zones | Metro Wide |  |  |  |  |  | 3,500 |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Conduct one rabies campaign in five sub-metros | Metro Wide |  |  |  |  |  | 5,000 |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Conduct carcass inspection at 4 slaughter slabs | Metro Wide |  |  |  |  |  | 2,000 |  |  |  | Agric Dept | Environmental Health |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Conduct CBP and PPR  vaccination for livestock’s | Metro Wide |  |  |  |  |  | 2,000 |  |  |  | Agric Dept | Environmental Health |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Sensitize and train 30 farmers to adopt preparation of urea treatment of maize Stover or rice straw | MOFA Office |  |  |  |  |  | 2,500 |  |  |  | Agric Dept | Environmental Health |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Sensitize 30 poultry and  livestock farmers on how to adopt various biosecurity and breed improvement | MOFA Office |  |  |  |  |  | 2,500 |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Train four hundred agro-input dealers on proper handling and storage of agro- inputs | MOFA Office |  |  |  |  |  | 3,500 |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Organize one sensitization programme for agro-input dealers on the need to regularize operating licenses. | MOFA Office |  |  |  |  |  | 2,000 |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Train hundred urban dwellers in the rudiments of urban gardening | MOFA Office |  |  |  |  |  | 2,500 |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Conduct sixteen (16)  demonstrations in urban  gardening in four (4) operational zones | Metro Wide |  |  |  |  | 2,000 |  |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Organize twelve (12) technical review meeting | MOFA Office |  |  |  |  | 1,000 |  |  |  |  | Agric Dept |  |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Organize Farmers Day celebration | Metro Wide |  |  |  |  |  | 50,000 |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Organize two (2) demonstrations on the production and use of orange flesh potatoes and on promotion of nutritious local leafy vegetables | Metro Wide |  |  |  |  | 2,500 |  |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Organize field trips and planning meetings with research extension linkages | Metro Wide |  |  |  |  | 1,500 |  |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Collect 52 weekly market commodity prices at four (4) major markets for dissemination | Metro Wide |  |  |  |  | 1,000 |  |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Organize 16 sensitization activities within the four (4) major market centers within the metropolis on grading and standardization of agricultural commodities. | Metro Wide |  |  |  |  |  | 5000 |  |  |  | Agric Dept | Beneficiaries |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Organize stakeholders meeting in collaboration with financial institutions | Metro Wide |  |  |  |  | 2,000 |  |  |  |  | Agric Dept | Beneficiaries |
| 4. Economic Development | SP 4.3  Development of Trade and Industry | Renovation of the Metro Agric Office Building | MOFA Office |  |  |  |  | 100,000 |  |  |  |  | Agric Dept | Works Dept. |
| **Development Dimension II – Social Development** | | | | | | | | | | | | | | |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Complete of 3No. Classroom Blocks in the Kumasi Metropolis | Santaase M/A/Adumanu M/A/Abrepo M/A |  |  |  |  |  | 1,500,000 |  |  |  | Education | Works | |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Rehabilitate 4No. classroom blocks | Wesco KG/ Wesco Pri. A&B, Higher Inst. Of Islam std/ Queen Elizabeth/Buokrom M/A |  |  |  |  | 100,000 | 400,000 |  |  |  | Education | Works | |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Construct 18Unit Classroom Block for community SHS at Ohwim | Ohwim |  |  |  |  |  | 1,200,000 |  |  |  | Education | Works |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Construct 2No. Fence wall around schools in the Kumasi Metropolis | Metro Wide |  |  |  |  |  | 600,000 |  |  |  | Education | Works |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Construct 1No. Astro Turf | Amakom |  |  |  |  |  | 400,000 |  |  |  | Education | Works |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Construct 50N0. Gender sensitive WASH facilities in basic /second cycle schools | Metro Wide |  |  |  |  |  | 10,000000 |  |  |  | Education | Works |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Procure 2000 school furniture for schools in the Kumasi Metropolis | Metro Wide |  |  |  |  |  | 500,000 |  |  |  | Education | Beneficiaries |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Procure and distribute Desktop Computers, Laptops and other ICT equipment to public Schools | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | Education | IT |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Procure and distribute 100 Dustbins and 10 Skip containers in schools | Metro Wide |  |  |  |  |  | 350,000 |  |  |  | Education | WMD |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Organize Capacity building workshop for all public basic school head teacher | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | Education | Head Teachers |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Organize Mock Exams for pupils in JHS in the Kumasi Metropolis | Metro Wide |  |  |  |  | 4,000 | 4,000 |  |  |  | Education |  |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Identify And select two Basic schools as Model schools in the Kumasi Metropolis | Asem/ |  |  |  |  | 2,000 | 2,000 |  |  |  | Education | Beneficiaries |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Support the organization of my First Day at School in 5 basic schools | Metro Wide |  |  |  |  | 2,500 | 3,000 |  |  |  | Education | Beneficiaries |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Support the organization of Metro Best Teachers’, Worker and School Award | Metro Wide |  |  |  |  | 5000 |  |  |  |  | Education | Beneficiaries |
| 3. Social Services Delivery | SP3.1 Education, Youth and Sports Management | Support the organization of STMIE Clinic for girls to promote Science, Mathematics and Technology | Metro Wide |  |  |  |  |  |  |  |  |  | Education | Beneficiaries |
| 3. Social Services Delivery | SP3.3 Health Services | Rehabilitate and furnish Moshie Zongo Health Centre | Moshie Zongo |  |  |  |  | 100,000 | 100,000 |  |  |  | Health | Works |
| 3. Social Services Delivery | SP3.3 Health Services | Construct 2No. Community Clinics and expand KMA clinic | Adoato/Duase/Adum |  |  |  |  |  | 1,500,000 |  |  |  | Health | Works |
| 3. Social Services Delivery | SP3.3 Health Services | Construct 1No. District and Psychiatric Hospital |  |  |  |  |  |  | 500,000 |  |  |  | Health | Works |
| 3. Social Services Delivery | SP3.3 Health Services | Support NID/ malarial control programme | Metro Wide |  |  |  |  |  | 3,500 |  |  |  | Health | Beneficiaries |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 3. Social Services Delivery | SP3.3 Health Services | Support cancer prevention programme (C- CAN) | Metro Wide |  |  |  |  |  | 3,000 |  |  |  | Health | Beneficiaries |
| 3. Social Services Delivery | SP3.3 Health Services | Introduce and promote telemedicine to improve health care services | Metro Wide |  |  |  |  | 2,500 |  |  |  |  | Health | Beneficiaries |
| 3. Social Services Delivery | SP3.3 Health Services | Organize one meeting annually between the Assembly and private health Operators for effective Health service delivery | Metro Wide |  |  |  |  | 4,500 |  |  |  |  | Health | Beneficiaries |
| 3. Social Services Delivery | SP3.3 Health Services | Organize stake holder meetings on safe motherhood and on appropriate nutrition -Iron folic supplementation | Metro Wide |  |  |  |  | 4,500 |  |  |  |  | Health | Beneficiaries |
| 3. Social Services Delivery | SP3.3 Health Services | Organize Monthly auditing of all maternal and neonatal deaths | Metro Wide |  |  |  |  | 2,000 |  |  |  |  | Health | Beneficiaries |
| 3. Social Services Delivery | SP3.3 Health Services | Screen OPD patients for high blood pressure  and organize annual health education on healthy lifestyle | Metro Wide |  |  |  |  |  | 4,500 |  |  |  | Health | Beneficiaries |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 3. Social Services Delivery | SP3.3 Health Services | Strengthen surveillance at all levels of service delivery and supervise facilities to ensure that emergency protocols are followed | Metro Wide |  |  |  |  | 2000 |  |  |  |  | Health | Beneficiaries |
| 3. Social Services Delivery | SP3.3 Health Services | Train more staff to test and treat TB cases | Metro Health Directorate |  |  |  |  |  | 5000 |  |  |  | Health | Beneficiaries |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Collect and analyze  data on persons/facilities  that generate waste, types  of waste generated and  mode of storage and  transport | Metro Wide |  |  |  |  |  | 25,000 |  |  |  | WMD | EHU |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Procure and distribute waste collection containers, PPEs, sanitary tools and motorized tricycles. | Metro Wide |  |  |  |  |  | 150,000 |  |  |  | WMD | EHU |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Build the capacity of EHOS/ Waste Management staff for effective sanitation service delivery | Main Admin |  |  |  |  |  | 5000 |  |  |  | WMD | HR |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Operate and maintain  Landfill site and Heavy  Duty Equipment | Oti |  |  |  |  | 20,000 | 50,000 |  |  |  | WMD | EHU |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Roll out a prog to promote waste segregation at source & sorting in basic sch. | Metro Wide |  |  |  |  | 3,000 |  |  |  |  | WMD | PRO |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Facilitate the conversion of wood waste from wood processing industries into pellets &briquettes | Metro Wide |  |  |  |  | 1,500 |  |  |  |  | WMD | EHU |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Implement Sanitation  Improvement Package  (SIP) with Zoomlion | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | WMD | Zoomlion |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Rezone operational areas of waste collection service providers | Metro Wide |  |  |  |  | 1,000 |  |  |  |  | WMD | SP |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Assess service providers  capacities and review  contracts | Metro Wide |  |  |  |  | 1,000 |  |  |  |  | WMD | SP |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Intensify promotion on the arrangements for HH toilets | Metro Wide |  |  |  |  |  | 3,000 |  |  |  | WMD | EHOs |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Issue abatement notice to landlords who have not initiated the process of constructing HH toilets & enforce the bye law by prosecuting recalcitrant ones | Metro Wide |  |  |  |  | 2,000 |  |  |  |  | WMD | EHOs |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Facilitate the Const. of 4000no. HH Toilets in low income HHs | Metro Wide |  |  |  |  | 2,500 |  |  |  |  | WMD | EHOs |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Organize quarterly inspection at all transfer stations and public toilets at sub-metro level | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | WMD | EHOs |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Construct 5No. Skip pads in selected communities &; Procure and distribute 30No. 13m3 Communal Containers | Metro Wide |  |  |  |  |  | 150,000 |  |  |  | WMD |  |
| 5. Environmental and Sanitation Management | SP5.2 Environmental Protection and Waste Management | Construct 1No. Waste transfer station at Asafo | Asafo |  |  |  |  |  | 150,000 |  |  |  | WMD | Works |
| 2. Infrastructure Delivery and Management | SP2.1 Public Works Service | Construct 5No. Mechanized Boreholes | AfiaKobi/Buokrom/Krofrom West/Afful Nkwanta/ N suntreso |  |  |  |  |  | 250000 |  |  |  | Works | Beneficiaries |
| 2. Infrastructure Delivery and Management | SP2.1 Public Works Service | Rehabilitate 2No. Mechanized Boreholes | Metro Wide |  |  |  |  |  | 20000 |  |  |  | Works | Beneficiaries |
| 2. Infrastructure Delivery and Management | SP2.1 Public Works Service | Extend water connections to 100 households | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | GWCL | Beneficiaries |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 2. Infrastructure Delivery and Management | SP2.1 Public Works Service | Train artisans on pipe connections and cleaning of overhead water tanks | Metro Wide |  |  |  |  |  | 10,000 |  |  |  | GWCL | Beneficiaries |
| 1.Management and Administration | SP1.1 General Administration | Sensitize and empower 8 women groups on Local Governance | Metro Wide |  |  |  |  | 4,500 |  |  |  |  | GDO | Beneficiaries |
| 1.Management and Administration | SP1.1 General Administration | Organize Training Workshop on the new Local Governance Act 936, 2016 for Assembly women & Unit Committee Members | Metro Wide |  |  |  |  |  | 5,000 |  |  |  | GDO | Beneficiaries |
| 1.Management and Administration | SP1.1 General Administration | Celebrate International Womens Day | Metro Wide |  |  |  |  |  | 3,000 |  |  |  | GDO | Beneficiaries |
| 1. Management and Administration | SP1.2 Planning and Coordination | Train HODs on mainstreaming of gender issues in planning and implementation of projects/activities | Metro Wide |  |  |  |  | 3000 |  |  |  |  | GDO | Beneficiaries |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Collect GPS data on the needy, vulnerable and marginalized and provide them with the needed support | Metro Wide |  |  |  |  | 2500 | 2500 |  |  |  | SW&CD | Beneficiaries |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Organize programmes for  20,000 persons with disabilities (PWDs) and their dependents and link them up to NHIS | Metro Wide |  |  |  |  | 1,500 | 1,500 |  |  |  | SW&CD | Beneficiaries |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Construct rehabilitation centre for vulnerable groups in Kumasi | Metro Wide |  |  |  |  |  | 200,000 |  |  |  | SW&CD | Works |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Construction of a Holding Centre/ Shelter for social victims | Metro Wide |  |  |  |  |  | 200,000 |  |  |  | SW&CD | Works |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Carry out sensitization programmes to benefit organized groups, school  children and general public | Metro Wide |  |  |  |  | 2000 |  |  |  |  | SW&CD |  |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Provide the needed support, skills and training to 300 poor, vulnerable and needy people | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | SW&CD | Beneficiaries |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Carry out LEAP activities to benefit 4000 beneficiaries | Metro Wide |  |  |  |  |  | 200,000 |  |  |  | SW&CD | Beneficiaries |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Render personal welfare  services to 5000 indigents and link them up to NHIS and other social interventions | Metro Wide |  |  |  |  | 3,000 |  |  |  |  | SW&CD | Beneficiaries |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Provide hospital welfare  services to 6800 patients | Metro Wide |  |  |  |  | 2000 |  |  |  |  | SW&CD |  |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Monitor the implementation of the GESP (Productive Inclusion) Project | Metro Wide |  |  |  |  |  | 5000 |  |  |  | SW&CD | Beneficiaries |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Support and re-integrate teenage pregnant girls back to school | Metro Wide |  |  |  |  | 1,500 |  |  |  |  | SW&CD | Beneficiaries |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Visit and educate 200  households on parental role on child management through child protection. | Metro Wide |  |  |  |  |  | 2000 |  |  |  | SW&CD | Beneficiaries |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Reunite children in residential homes with their families and relations | Metro Wide |  |  |  |  | 1,000 |  |  |  |  | SW&CD | Beneficiaries |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Monitor the growth and  development of children in Residential Home for children | Metro Wide |  |  |  |  |  | 1,500 |  |  |  | SW&CD |  |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Undertake case  management to strengthen  families | Metro Wide |  |  |  |  | 1,000 |  |  |  |  | SW&CD |  |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Organize talk sessions on  child abuse, labor and  molestation in 80 schools | Metro Wide |  |  |  |  |  | 3000 |  |  |  | SW&CD | Beneficiaries |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Highlight the responsibilities  of the parents and children at  home and in schools within 80 selected schools and religious groups. | Metro Wide |  |  |  |  | 2500 |  |  |  |  | SW&CD | Beneficiaries |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Monitor, register and  renew certificates and organize training for 390 day centers | Metro Wide |  |  |  |  |  | 2000 |  |  |  | SW&CD |  |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Provide the needed support and skills training for the selected children and families | Metro Wide |  |  |  |  |  | 3500 |  |  |  | SW&CD |  |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** | |
| 3. Social Services Delivery | SP3.2 Social Welfare and Community Development | Train the 200 youth in entrepreneurship and alternative means of gainful employment as well as linking them to gov’t job creation interventions including NEIP, Planting for food and jobs, etc. | Metro Wide |  |  |  |  | 5000 |  |  |  |  | SW&CD |  | |
| **Development Dimension III – Environment, Infrastructure, Energy and Human Settlement** | | | | | | | | | | | | | | | |
| 2. Infrastructure Delivery and Management | SP2.3 Physical & Spatial Planning Department | Identify, verify and acquire lease on all lands zoned for public use across the metropolis (phase 1) | Metro Wide |  |  |  |  |  | 10,000 |  |  |  | Physical Planning | Traditional Authority | |
| 2. Infrastructure Delivery and Management | SP2.3 Physical & Spatial Planning Department | Organize sensitization campaigns to educate the public on building on unauthorized areas | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | Physical Planning | PRO | |
| 2. Infrastructure Delivery and Management | SP2.3 Physical & Spatial Planning Department | Carry out mop-up data collection exercise for Manhyia, Nhyiaeso and Bantama Sub-metros to complete SNPA | Manhyia Sub-metro/  Nhyiaeso Sub-metro/ Bantama Sub - metro |  |  |  |  | 4,000 |  |  |  |  | Physical Planning | Revenue Unit | |
| 2. Infrastructure Delivery and Management | SP2.3 Physical & Spatial Planning Department | Prepare 2 rectification plans per quarter for three years. | Metro Wide |  |  |  |  |  | 5000 |  |  |  | Physical Planning |  | |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** | |
| 2. Infrastructure Delivery and Management | SP2.3 Physical & Spatial Planning Department | Develop local plan for CBD of Kumasi including construction policy | Adum |  |  |  |  |  | 5,000 |  |  |  | Physical Planning |  | |
| 5. Environmental and Sanitation Management | SP5.3 Natural Resources Conservation | Construct Community Centre | Abrepo Junction |  |  |  |  |  | 200,000 |  |  |  | Works |  | |
| 2. Infrastructure Delivery and Management | SP2.3 Physical & Spatial Planning Department | Implement KMA/VNG International Deals Project | Metro Wide |  |  |  |  |  | 100,000 |  |  |  | Planning Unit | Transport/ PPD | |
| 5. Environmental and Sanitation Management | SP5.3 Natural Resources Conservation | Sensitize the public on acquisition of land and permitting procedures | Metro Wide |  |  |  |  | 3,000 |  |  |  |  | Works | PRO | |
| 2. Infrastructure Delivery and Management | SP2.1 Public Works Service | Organize periodic monitoring exercises to ensure Conformity to standards by developers (Enforcement) | Metro Wide |  |  |  |  | 3,000 |  |  |  |  | Works | SPC | |
| 2. Infrastructure Delivery and Management | SP2.1 Public Works Service | Procure working tools (Schmidt hammer, Wheel measuring roller, electrical tools, maintenance tools) for effective supervision | Metro Wide |  |  |  |  |  | 10,000 |  |  |  | Works |  | |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** | |
| 5. Environmental and Sanitation Management | SP5.3 Natural Resources Conservation | Collaborate with other institutions to introduce renewable energy system in the metropolis | Metro Wide |  |  |  |  | 2,000 |  |  |  |  | Works |  | |
| 2. Infrastructure Delivery and Management | SP2.2 Urban Roads Management | Procure and Distribute 3,200 complete Street lights in the Kumasi Metropolis | Metro Wide |  |  |  |  |  | 500,000 |  |  |  | Works | Assembly Members | |
| 2. Infrastructure Delivery and Management | SP2.2 Urban Roads Management | Construct 2N0. Multi-storey Car parks - Adum | Adum  Central Market |  |  |  |  |  |  | 2,000,000 |  |  | Works | Beneficiaries | |
| 2. Infrastructure Delivery and Management | SP2.2 Urban Roads Management | Construct 2No. Metal footbridges and Drains in 6 communities | Dakwadwom Abrepo Junc.  Moshie Zongo Doti/Krofrom E  FNT/Duase/ |  |  |  |  |  | 850000 |  |  |  | Metro Roads |  | |
| 2. Infrastructure Delivery and Management | SP2.2 Urban Roads Management | Rehabilitate 1No. Metal Footbridges | Buokrom South Africa |  |  |  |  |  | 50,000 |  |  |  | Metro Roads |  | |
| 4. Economic Development | SP4.2 Transport and Traffic Management | Carry out operational  activities to improve  upon public transport  services &urban mobility | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | Transport Dept. | MTTD | |
| 4. Economic Development | SP4.2 Transport and Traffic Management | Develop proposal to  institute modalities for  the operationalization of  mass transit system | Metro Wide |  |  |  |  | 2,000 |  |  |  |  | Transport Dept. | Planning Unit | |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** | |
| 4. Economic Development | SP4.2 Transport and Traffic Management | Implement the AFD  sponsored ASToN and  MYC projects | Metro Wide |  |  |  |  |  | 15,000 |  |  |  | Transport Dept. |  | |
| 4. Economic Development | SP4.2 Transport and Traffic Management | Implement the  partnership for Healthy  Cities Road Safety  project/ BIGRS | Metro Wide |  |  |  |  |  | 10,000 |  |  |  | Transport Dept. |  | |
| 4. Economic Development | SP4.2 Transport and Traffic Management | Carryout monthly  monitoring and  evaluation of activities | Metro Wide |  |  |  |  | 6,000 |  |  |  |  | Transport Dept. |  | |
| 1.Management and Administration | SP1.1 General Administration | Collaborate with the Ministry of Communication/NCA to improve the network connectivity in the metropolis | Metro Wide |  |  |  |  | 2,000 |  |  |  |  | IT Unit | Beneficiaries | |
| 4. Economic Development | SP 4.1  Development of Trade and Industry | Invest in broadband internet infrastructure to support uptake of e-commerce at the Central Business District | Metro Wide |  |  |  |  |  | 20,000 |  |  |  | IT Unit | Beneficiaries | |
| 5. Environmental and Sanitation Management | SP5.3 Natural Resources Conservation | Plant and Nurture to growth 10,000 trees in schools, communities and along major routes | Metro Wide |  |  |  |  |  | 5000 |  |  |  | Forestry | Environmental Health Unit | |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** | |
| **Dimension IV: Governance, Corruption and Public Accountability** | | | | | | | | | | | | | | | |
| 1.Management and Administration | SP1.1 General Administration | Organize 2no Town hall meetings annually to account community members on the implementation of Assembly programmes and activities | Prempeh Assembly Hall |  |  |  |  |  | 25,000 |  |  |  | Planning Unit | | Budget & Ratings |
| 1.Management and Administration | SP1.1 General Administration | Construct and furnish 1No. Sub – Metro Office | Manhyia North |  |  |  |  |  | 300,000 |  |  |  | Works | | Beneficiaries |
| 1.Management and Administration | SP1.1 General Administration | Complete the construction of 1No. Sub metro | Bantama |  |  |  |  |  | 250,000 |  |  |  | Works | | Beneficiaries |
| 1.Management and Administration | SP1.1 General Administration | Organize talk shows at radio stations to explain the services provided by the Assembly & how to access them | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | PRO | | ISD |
| 1.Management and Administration | SP1.1 General Administration | Organize MCE’s electoral area tour | Metro Wide |  |  |  |  | 5,000 | 5,000 |  |  |  | PRO | | ISD |
| 1.Management and Administration | SP1.1 General Administration | Develop service charter to enhance information flow and service delivery | Metro Wide |  |  |  |  |  | 10,000 |  |  |  | Central Admin | |  |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** | |
| 1.Management and Administration | SP1.1 General Administration | Organize training for Assembly members on key areas of the Assembly’s operations | Prempeh Assembly Hall |  |  |  |  |  | 5000 |  |  |  | HR | |  |
| 6. Budget and Finance | SP6.3 Revenue Mobilization and Management | Deploy DLREV (Ntobua) software for collection of revenue data, issuance and distribution of bills | Main Admin |  |  |  |  | 2000 |  |  |  |  | Finance | | Budget |
| 6. Budget and Finance | SP6.3 Revenue Mobilization and Management | Purchase and utilize 50No. Point of Sale (POS) devices for collection of all revenue | Metro Wide |  |  |  |  |  | 20,000 |  |  |  | Finance | | Budget |
| 6. Budget and Finance | SP6.3 Revenue Mobilization and Management | Train revenue collectors and finance staff on new IT system and effective revenue collection | Prempeh Assembly Hall |  |  |  |  |  | 10,000 |  |  |  | HR | | Finance |
| 6. Budget and Finance | SP6.3 Revenue Mobilization and Management | Update new property values for collection | Main Admin |  |  |  |  | 2000 |  |  |  |  | Finance | |  |
| 6. Budget and Finance | SP6.3 Revenue Mobilization and Management | Provide IT system to link centralized departments to the revenue unit | Metro Wide |  |  |  |  |  | 15,000 |  |  |  | IT | | Finance |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** | |
| 6. Budget and Finance | SP6.3 Revenue Mobilization and Management | Organize radio programs monthly to educate tax payers about the need to pay taxes | Metro Wide |  |  |  |  | 5000 |  |  |  |  | Finance | | PRO |
| 6. Budget and Finance | SP6.3 Revenue Mobilization and Management | Organize stakeholder engagements with the business community on Fee fixing resolution annually | Prempeh Assembly Hall |  |  |  |  | 5000 | 5000 |  |  |  | Budget | | Finance |
| 6. Budget and Finance | SP6.3 Revenue Mobilization and Management | Review Budget at Mid- year and prepare revenue improvement action plan | Metro Wide |  |  |  |  | 3000 |  |  |  |  | Budget | | Finance |
| 6. Budget and Finance | SP6.3 Revenue Mobilization and Management | Review/Update data for budget and ratings and integrate IT in budget monitoring and performance analysis | Metro Wide |  |  |  |  | 2000 |  |  |  |  | Budget | | IT |
| 1.Management and Administration | SP1.1 General Administration | Construct and furnish 1No. Police Station at Asafo | Metro Wide |  |  |  |  |  | 400000 |  |  |  | Legal | | Works |
| 1.Management and Administration | SP1.1 General Administration | Construct 1No. Police Quarters at Subin Valley | Subin Valley |  |  |  |  |  | 300000 |  |  |  | Legal | | Works |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** | |
| 1.Management and Administration | SP1.5 Human Resource | Prepare training needs assessment and organize Quarterly Capacity Building workshop for staff | Metro Wide |  |  |  |  |  | 20,000 |  |  |  | HR | |  |
| 1.Management and Administration | SP1.1 General Administration | Complete District level Census report | Metro Wide |  |  |  |  |  | 10000 |  |  |  | Statistics | | Planning Unit |
| 1.Management and Administration | SP1.1 General Administration | Disseminate & organize stakeholder engagement on the 2021 Census report | Metro Wide |  |  |  |  |  | 10,000 |  |  |  | Statistics | | PRO |
| **Development Dimension V: Emergency planning and response (including covid-19 recovery plan)** | | | | | | | | | | | | | | | |
| 5. Environment and Sanitation | SP5.1  Disaster Development and Management | Organize educational campaigns on fire and floods for all filling stations in the Kumasi Metropolis | Metro Wide |  |  |  |  | 2500 | 3000 |  |  |  | NADMO | | Fire Service/ WMD |
| 5. Environment and Sanitation | SP5.1  Disaster Development and Management | Carryout inspection and evaluation of public/private facilities to ensure safety | Metro Wide |  |  |  |  | 3000 |  |  |  |  | NADMO | | Works |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Programme**  **(PBB)** | | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 5. Environment and Sanitation | SP5.1  Disaster Development and Management | | Desilt chocked drains and streams | Metro Wide |  |  |  |  |  |  |  |  |  | NADMO | Works/Urban Roads |
| 5. Environment and Sanitation | SP5.1  Disaster Development and Management | | Build the Capacity of NADMO Staff in disaster management | Metro Wide |  |  |  |  | 2000 |  |  |  |  | NADMO | HR |
| 5. Environment and Sanitation | | SP5.1  Disaster Development and Management | Organize celebration of World Disaster Day | Metro Wide |  |  |  |  |  | 4000 |  |  |  | NADMO |  |
| 1.Management and Administration | | SP1.1 General Administration | Design and distribute COVID – 19 messages targeting the blind and deaf | Metro Wide |  |  |  |  |  | 5000 |  |  |  | Environmental Health Unit | PRO |
| 1.Management and Administration | | SP1.1 General Administration | Support artisans to enable them manufacture machines and equipment for local manufacturing companies | Metro Wide |  |  |  |  |  | 2,000,000 |  |  |  | Trade & Investment committee |  |
| 1.Management and Administration | | SP1.1 General Administration | Organize bi-annual platform for engaging private formal and informal on the growth of local businesses | Metro Wide |  |  |  |  |  | 10,000.00 |  |  |  | Trade & Investment committee |  |
| 1.Management and Administration | | SP1.1 General Administration | Support deaf and blind to acquire modern technological gadgets to facilitate their learning and education | Metro Wide |  |  |  |  |  | 50,000 |  |  |  | Social Welfare | Education |
| 1.Management and Administration | | SP1.1 General Administration | Integrate PWDs in into for formal public schools to obtain employable skills | Metro Wide |  |  |  |  |  |  |  |  |  | Social Welfare | Education |
| 1.Management and Administration | | SP1.1 General Administration | Facilitate support mechanism for private schools, including teachers | Metro Wide |  |  |  |  |  | 20,000 |  |  |  | Education |  |
| 1.Management and Administration | | SP1.1 General Administration | Explore support mechanism for private health facilities, including workers | Metro Wide |  |  |  |  |  | 500, 000 |  |  |  | Health |  |
| 1.Management and Administration | | SP1.1 General Administration | Expand access to food storage warehouses | Metro Wide |  |  |  |  |  | 1,000,000 |  |  |  | Agric |  |
| 1.Management and Administration | | SP1.1 General Administration | Invest in broadband internet infrastructure to support uptake of e-commerce at the Central Business District | Metro Wide |  |  |  |  |  | 1,000,000.00 |  |  |  | Trade & Investment committee |  |
| 1.Management and Administration | | SP1.1 GeneralAdministration | Construct infectious centre at Suntreso Hospital | Metro Wide |  |  |  |  |  | 1,000,000.00 |  |  |  | Health |  |
| 1.Management and Administration | | SP1.1 GeneralAdministration | Initiate renewable energy projects to ensure reliable power supply | Metro Wide |  |  |  |  |  | 1,000,000.00 |  |  |  | Works |  |
| 1.Management and Administration | | SP1.1 GeneralAdministration | Invest in functional ICT systems in response to all pandemic | Metro Wide |  |  |  |  |  | 40,000 |  |  |  | Education |  |
| **Programme**  **(PBB)** | | **Sub-Programme**  **(PBB)** | **Activities** | **Location** | **2022** | | | | **Cost** | | | **Programme Status** | | **Implementing**  **Institution/Department** | |
| **Q1** | **Q2** | **Q3** | **Q4** | **IGF** | **GOG** | **Others** | **New** | **Ongoing** | **Lead** | **Collaborating** |
| 1.Management and Administration | | SP1.1 General Administration | Institutionalize emergency response teams across all institutions | Metro Wide |  |  |  |  |  | 50,000 |  |  |  | Central Admin |  |
| **Development Dimension VI: Implementation, coordination, monitoring and evaluation** | | | | | | | | | | | | | | | |
| 1. Management and Administration | | SP1.2 Planning and Coordination | Organize capacity building workshop on Monitoring and Evaluation for Assembly Staff | Metro Wide |  |  |  |  |  | 5000 |  |  |  | HR |  |
| 1. Management and Administration | | SP1.2 Planning and Coordination | Prepare and update M&E Plan for MTDP | Metro Wide |  |  |  |  | 5000 |  |  |  |  | MPCU |  |
| 1. Management and Administration | | SP1.2 Planning and Coordination | Conduct routine monitoring of Assembly’s on-going projects and programs | Metro Wide |  |  |  |  |  | 40,000 |  |  |  | MPCU |  |
| 1. Management and Administration | | SP1.2 Planning and Coordination | Organise quarterly MPCU meetings | Metro Wide |  |  |  |  |  | 20,000 |  |  |  | MPCU |  |
| 1. Management and Administration | | SP1.2 Planning and Coordination | Organize participatory M&E on assembly activities | Metro Wide |  |  |  |  |  | 20,000 |  |  |  | MPCU |  |