#### KUMASI METROPOLITAN ASSEMBLY

#### 2025 ANNUAL ACTION PLAN

| Programme (PBB) | Sub-Programme (PBB) | Activities |  | Location | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |
| Development Dimension I – Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Economic Development | SP 4.1 Development of Trade and Industry | Update data on Businesses in Kumasi |  | Metro Wide |  |  |  |  | 20,000 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |  |
| 4. Economic Development | SP 4.1 Development of Trade and Industry | Organize a business forum to enhance public and private sector synergies |  |  |  |  |  |  | 10,000 | 20,000 |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |  |
| 4. Economic Development | SP 4.1 Development of Trade and Industry | Facilitate and support formalization of informal SMEs |  | Metro Wide |  |  |  |  | 1,000 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |  |
| 4. Economic Development | SP 4.1 Development of Trade and Industry | Organize training on on-line sales for SMEs |  | Metro Wide |  |  |  |  | 10,000 |  |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |  |
| 4. Economic Development | SP 4.1 Development of Trade and Industry | Develop comprehensive LED strategy |  | Metro Wide |  |  |  |  | 4,000 | 16,000 |  |  |  | Trade & Investment committee | NBSSI, ASSI, AGI |  |
| 4. Economic Development | SP 4.2 Tourism Development | Organize quarterly radio-talk show on the potentials of local tourism |  | Metro Wide |  |  |  |  | 4000 | 4000 |  |  |  | Trade & Investment | GTA |  |
| 4. Economic Development | SP 4.2 Tourism Development | Institute and organise annual home coming carnival |  | Metro Wide |  |  |  |  | 10,000 | 40,000 |  |  |  | Trade & Investment committee | GTA |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities |  | Location | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |
| 4. Economic Development | SP 4.3 Development of Trade and Industry | 12 AEAs to conduct home and farm visit to advice 40% females and 60% males farmers, weekly market survey by the end of the year. |  | Metro Wide |  |  |  |  |  | 20,000 |  |  |  | Agric Dept | Market Queens |  |
| 4. Economic Development | SP 4.3 Development of Trade and Industry | 7 MOAs to visit AEAs under their supervision to guide and offer technical backstopping. |  | Metro Wide |  |  |  |  |  | 20,000 |  |  |  | Agric Dept | Beneficiaries |  |
| 4. Economic Development | SP 4.3 Devt of Trade and Industry | Director of Agric and MCE to conduct 12 M&E activities |  | Metro Wide |  |  |  |  | 12,000 |  |  |  |  | Agric Dept | Beneficiaries |  |
| 4. Economic Development | SP 4.3 Devt of Trade and Industry | Organise 10 organic vegetables demonstration. |  | Metro Wide |  |  |  |  |  | 20000 |  |  |  | Agric Dept | Beneficiaries |  |
| 4. Economic Development | SP 4.3 Devt of Trade and Industry | Organize 5 rabies vaccination campaign in the 5 Sub-metros |  | Metro Wide |  |  |  |  | 15000 |  |  |  |  | Agric Dept | Beneficiaries |  |
| 4. Economic Development | SP 4.3 Devt of Trade and Industry | Organize Farmers Day celebration |  | Metro Wide |  |  |  |  |  | 70,000 |  |  |  | Agric Dept | Beneficiaries |  |
| 4. Economic Development | SP 4.3 Devt of Trade and Industry | Organize stakeholders meeting in collaboration with financial institutions |  | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | Agric Dept | Beneficiaries |  |
| 4. Economic Development | SP 4.3 Devt of Trade and Industry | Renovation of the Metro Agric Office Building |  | MOFA Office |  |  |  |  |  | 500,000 |  |  |  | Agric Dept | Works Dept. |  |
| 4. Economic Development | SP 4.3 Development | Train 25 Youth on Poultry Production |  | Metro Wide |  |  |  |  |  | 4,000 |  |  |  | Agric Dept | Environmental Health |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities |  | Location | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |
| 4. Economic Development | SP 4.3 Development of Trade and Industry | Weekly disease surveillance on: Avian Influenza, Rabies, Pest de Petit Ruminal and CBPP |  | Metro Wide |  |  |  |  | 6,000 |  |  |  |  | Agric Dept | Works Dept. |  |
| 4. Economic Development | SP 4.3 Development of Trade and Industry | Organize one training session for 30 women in 4 basic schools undertaking school feeding program |  | MOFA Office |  |  |  |  | 4,000 |  |  |  |  | Agric Dept | Works Dept. |  |
| 4. Economic Development | SP 4.3 Devt of Trade and Industry | Organise four plant clinics for women farmers at four different operational areas. |  | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | Agric Dept | Works Dept. |  |
| 4. Economic Development | SP 4.3 Development of Trade and Industry | Organize monthly technical review meetings for 25 staff (6 females and 21 males). |  | MOFA Office |  |  |  |  | 10,000 |  |  |  |  | Agric Dept | Works Dept. |  |
| 4. Economic Development | SP 4.3 Development of Trade and Industry | Organize one plg session for 30 stakeholders with at least 35% female participation. |  | MOFA Office |  |  |  |  | 6,000 |  |  |  |  | Agric Dept | Works Dept. |  |
| 4. Economic Development | SP 4.3 Development of Trade and Industry | Organize training for 20 women vegetable traders on grading, standardization and packaging |  | Bantama and Abinkyi |  |  |  |  |  | 3000 |  |  |  | Agric Dept | Market women |  |
| 4. Economic Development | SP 4.3 Devt of Trade and Industry | Organize 6 trainings for 120 agric commodity-based women traders on post harvest loses |  | Bantama and Abinkyi |  |  |  |  |  | 10000 |  |  |  | Agric Dept | Market women |  |
| 4. Economic Development | SP 4.3 Devt of Trade and Industry | Rehabilitate 1No. Market and Construct 24Hour Economy Market |  | Race Course Krofofrom |  |  |  |  |  | 9,000,000 |  |  |  | Agric Dept | Works Dept Market women |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities |  | Location | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |
| Development Dimension II – Social Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Social Services Delivery | SP2.1 Education, Youth | Construct 2No. Classroom Blocks |  | Santaasi M/A Adumanu Phase II |  |  |  |  | 1,500,000 |  |  |  |  | Education | Works |  |
| 2. Social Services Delivery | SP2.1 Education, Youth | Rehabilitate 7N0. Classroom Blocks and Construct 1No. KG |  | Asem Opoku Ware Basic |  |  |  |  |  | 1,600.000 |  |  |  | Education | Works |  |
| 2. Social Services Delivery | SP2.1 Education, Youth | Construct 2No. 6Unit Classroom Blocks |  | Adabiya Islamic Adiebeba M/A |  |  |  |  |  | 1,500,000 |  |  |  | Education | Works |  |
| 2. Social Services Delivery | SP2.1 Education, Youth | Procure 7000 school furniture for schools |  | Metro Wide |  |  |  |  |  | 3,200.000 |  |  |  | Education | Beneficiaries |  |
| 2. Social Services Delivery | SP2.1 Education, Youth and Sports Services | Provide Sponsorship for 200 (120 girls and 80 boys) needy but brilliant students |  | Metro Wide |  |  |  |  |  | 150,000 |  |  |  | Education | Head Teachers |  |
| 2. Social Services Delivery | SP2.1 Education, Youth an | Organize Mock Exams for pupils in JHS in the Kumasi Metropolis |  | Metro Wide |  |  |  |  | 10,000 | 25,000 |  |  |  | Education |  |  |
| 2. Social Services Delivery | SP2.1 Education, Youth | Organize reading festival to promote early grade reading |  | Asem/ |  |  |  |  | 2,000 | 33000 |  |  |  | Education | Beneficiaries |  |
| 2. Social Services Delivery | SP2.1 Education, Youth and | Support the organization of my First Day and National Day celebrations |  | Metro Wide |  |  |  |  | 10,000 | 150,000 |  |  |  | Education | Beneficiaries |  |
| 2. Social Services Delivery | SP2.1 Education, Youth and | Support the organization of Metro Best Teachers’, Worker and School Award |  | Metro Wide |  |  |  |  | 45000 |  |  |  |  | Education | Beneficiaries |  |
| 2. Social Services Delivery | SP2.1 Education, Youth and Sports Services | Support the organization of STMIE Clinic for girls to promote Science, Mathematics and Tech |  | Metro Wide |  |  |  |  | 47500 |  |  |  |  | Education | Beneficiaries |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities |  | Location | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| 2. Social Services Delivery | SP2.2 Health Services and Management | Rehabilitate and furnish Moshie Zongo Health Centre and Construct Pedeatric Centre (CHPS) |  | Moshie Zongo Adum |  |  |  |  | 1,500,000 | 2,700,00 |  |  |  | Health | Works |  |  |
| 2. Social Services Delivery | SP2.2 Health Services and Management | Support NID/ malarial control programme |  | Metro Wide |  |  |  |  |  | 4000 |  |  |  | Health | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.2 Health Services and Management | Support cancer prevention programme (C- CAN) |  | Metro Wide |  |  |  |  |  | 4000 |  |  |  | Health | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.2 Health Services and Management | Introduce and promote telemedicine to improve health care services |  | Metro Wide |  |  |  |  | 3,000 |  |  |  |  | Health | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.2 Health Services and Management | Organize HIV/AIDS awareness program |  | Metro Wide |  |  |  |  |  | 150,000 |  |  |  | Health | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.2 Health Services and Management | Organize one meeting annually between the Assembly and private health Operators for effective Health service delivery |  | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | Health | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.2 Health Services and Management | Organize stake holder meetings on safe motherhood and on appropriate nutrition -Iron folic supplementation |  | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | Health | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.2 Health Services and Management | Screen OPD patients for HBP and organize annual education on healthy lifestyle |  | Metro Wide |  |  |  |  |  | 4,500 |  |  |  | Health | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.2 Health Services and Management | Train more staff to test and treat TB cases 14 |  | Metro Health Directorate |  |  |  |  |  | 5000 |  |  |  | Health | Beneficiaries |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities |  | Location | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| 2. Social Services Delivery | SP2.2 Health Services and Management | Strengthen surveillance and supervise facilities to ensure that emergency protocols are followed |  | Metro Wide |  |  |  |  | 2000 |  |  |  |  | Health | Beneficiaries |  |  |
| 5. Environmental and Sanitation Management | SP5.3 Environmental Protection and Waste Management | Construct 5No. Skip Pads & supply 5No. 14 Containers |  | Metro Wide |  |  |  |  |  | 650,000 |  |  |  | WMD | EHU |  |  |
| 5. Environmental and Sanitation Management | SP5.3 Environmental Protection and Waste Management | Procure and distribute waste collection containers, PPEs, sanitary tools and motorized tricycles. |  | Metro Wide |  |  |  |  |  | 200,000 |  |  |  | WMD | EHU |  |  |
| 5. Environmental and Sanitation Management | SP5.3 Environmental Protection and Waste Management | Build the capacity of EHOS/ Waste Management staff for effective sanitation service delivery |  | Main Admin |  |  |  |  |  | 10,000 |  |  |  | WMD | HR |  |  |
| 5. Environmental and Sanitation m | SP5.3 Environmental Protection and Waste Magt | Operate and maintain Landfill site and Heavy Duty Equipment/ Construction of Re-enforced Concrete Head Wall |  | Oti |  |  |  |  | 350000 | 280,000 |  |  |  | WMD | EHU |  |  |
| 5. Environmental and Sanitation Ma | SP5.3 Environmental Protection and Waste Magt | Roll out a prog to promote waste segregation at source & sorting in selected communities and schools |  | Metro Wide |  |  |  |  | 3,000 |  |  |  |  | WMD | EHOs |  |  |
| 5. Environmental and Sanitation Management | SP5.3 Environmental Protection and Waste Management | Implement Sanitation Improvement Package (SIP) and Fumigation |  | Metro Wide |  |  |  |  |  | 1,200.000 |  |  |  | WMD | Zoomlion |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities |  | Location | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| 5. Environmental and Sanitation | SP5.3 Environmental Protection and Waste Magt | Assess service providers capacities and Monitor their operations |  | Metro Wide |  |  |  |  | 2,000 |  |  |  |  | WMD | SP |  |  |
| 5. Environmental and Sanitation | SP5.3 Environmental Protection and Waste Mana | Issue Abatement notice to homeowners without toilet facilities |  | Metro Wide |  |  |  |  |  | 5,000 |  |  |  | WMD | EHOs |  |  |
| 5. Environmental and Sanitation M | SP5.3 Environmental Protection and Waste Magt | Facilitate the Const. of 200no. HH Toilets in low income HHs |  | Metro Wide |  |  |  |  | 20,000 |  |  |  |  | WMD | EHOs |  |  |
| 5. Environmental and Sanitation | SP5.3 Environmental Protection and Waste Mana | Organize 20 Community Durbars and 20 clean up campaigns |  | Metro Wide |  |  |  |  | 50,000 |  |  |  |  | WMD | EHOs |  |  |
| 5. Environmental and Sanitation | SP5.3 Environmental Protection and Waste Mangt | Organize quarterly inspection at all transfer stations and public toilets at sub-metro level |  | Metro Wide |  |  |  |  | 4,000 |  |  |  |  | WMD | EHOs |  |  |
| 5. Environmental and Sanitation Management | SP5.3 Environmental Protection and Waste Management | Calibrate noise emitting devices of new 120 institutions and carry out 12 radio educational programmes on envt |  | Metro Wide |  |  |  |  | 20,000 | 10,000 |  |  |  | WMD |  |  |  |
| 5. Environmental and Sanitation M | SP5.3 Environmental Protection and Waste Mangt | Support for the Rehabilitation and expansion of 2No. Sewage Ponds |  | Asafo Adum |  |  |  |  | 50,000 |  |  |  |  | WMD | Works |  |  |
| 5. Environmental and Sanitation M | SP5.3 Environmental Protection and Waste Mangt | Organize food hygiene education for school feeding caterers and conduct routine food handler screening and certification |  | Metro Wide |  |  |  |  | 30,000 |  |  |  |  | WMD | EHU |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities |  | Location | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| 5. Environmental and Sanitation M | SP5.3 Environmental Protection and Waste Mangt | Intensify premises inspection and environmental Health Sanitation prosecutions |  | Metro Wide |  |  |  |  | 5000 |  |  |  |  | WMD | EHU |  |  |
| 3. Infrastructure Delivery and Management | SP3.1 Public Works, Rural Housing & Water Magt | Construct 10No. Mechanized Boreholes and repair and maintain 5No. (Metro Wide) |  | Daban/Patasi/Kokoso/AbrepMpatasie/ N suntreso/MBD |  |  |  |  |  | 700,000 |  |  |  | Works | Beneficiaries |  |  |
| 1.Management and Administratio | SP1.1 General Administration | Organize activities to celebrate Breast Cancer Awareness Month |  | Metro Wide |  |  |  |  | 10,000 | 10000 |  |  |  | GDO | Beneficiaries |  |  |
| 1. Management and Adminis | SP1.2 Planning and Coordination | Train HODs on mainstreaming of gender issues in planning and project implementation |  | Metro Wide |  |  |  |  | 5500 |  |  |  |  | GDO | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Community Development | Collect GPS data on needy, vulnerable and marginalized and provide them with support |  | Metro Wide |  |  |  |  | 4000 | 2000 |  |  |  | SW&CD | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Community Development | Organize programmes for 60 PWDs and their dependents and link them up to NHIS |  | Metro Wide |  |  |  |  | 3,500 | 7,500 |  |  |  | SW&CD | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Community Development | Sensitize 3 women groups on Gender Based Violence and its preventive measures |  | Metro Wide |  |  |  |  | 5000 |  |  |  |  | SW&CD |  |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Community De | Organize educational program for children on rights and responsibilities |  | Metro Wide |  |  |  |  | 5,000 | 1,000 |  |  |  | SW&CD | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Community | Carry out LEAP activities to benefit 3150 beneficiaries, through home visits and referral |  | Metro Wide |  |  |  |  | 2,000 | 20,000 |  |  |  | SW&CD | Beneficiaries |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities |  | Location | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Community Development | Render personal welfare services to 40 indigents and link them up to NHIS and other social intervent |  | Metro Wide |  |  |  |  | 5,000 |  |  |  |  | SW&CD | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Comty Devt | Provide hospital welfare services to 30 patients |  | Metro Wide |  |  |  |  | 2000.00 | 5,000.00 |  |  |  | SW&CD |  |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Community D | Reunite children in residential homes with their families and relations |  | Metro Wide |  |  |  |  | 3,000 | 3000 |  |  |  | SW&CD | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Community Development | Educate 20 teenage Head Porters (Kayaye) leaders on personal care, health, rights and others |  | Metro Wide |  |  |  |  | 3,000.00 | 1,500 |  |  |  | SW&CD |  |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Community Development | Undertake case mangt to strengthen Families for the benefit 60 children/clients |  | Metro Wide |  |  |  |  | 5000 | 15,000.00 |  |  |  | SW&CD |  |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Comt Det | Organize talk sessions on child abuse, time mangt, labor and molestation for students |  | Metro Wide |  |  |  |  | 3000 | 3000 |  |  |  | SW&CD | Beneficiaries |  |  |
| 2. Social Services Delivery | SP2.3 Social Welfare and Community Development | Monitor, register and renew certificates and organize training for 30 day centers and 30 NPOs/NGOs |  | Metro Wide |  |  |  |  | 4000 | 2000 |  |  |  | SW&CD |  |  |  |
| 2. Social Services Delivery | SP2.4 Birth & Death Registration | Organize Mobile and mob up registration of Birth and Death |  | Atasomanso, Sepe, Dichemso, Keje |  |  |  |  |  | 4500 |  |  |  | Birth and Death | MPCU |  |  |
| 2. Social Services Delivery | SP2.4 Birth & Death Registration | Organize Birth and Deaths Week Celebration |  | Ahodwo, Sokoban, Adiebeba |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities | Location |  | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| Development Dimension III – Environment, Infrastructure, Energy and Human Settlement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Infrastructure Delivery and Management | SP2.3 Physical & Spatial Planning Development | Identify, verify and acquire lease on all lands zoned for public use across the metropolis (phase 1) | Metro Wide |  |  |  |  |  |  | 70,000 |  |  |  | Physical Planning | Traditional Authority |  |  |
| 3. Infrastructure Delivery and Management | SP2.3 Physical & Spatial Planning Development | Organize sensitization campaigns to educate the public on building on unauthorized areas | Metro Wide |  |  |  |  |  | 4,000 |  |  |  |  | Physical Planning | PRO |  |  |
| 3Infrastructure Delivery and Mangt | SP2.3 Physical & Spatial Planning Devt | Sensitize the public on acquisition of land and permitting procedures | Metro Wide |  |  |  |  |  | 3,000 |  |  |  |  | Physical Planning | PRO |  |  |
| 3. Infrastructure Delivery and Management | SP3.2 Public Works, Rural Housing & Water mgt | Organize periodic monitoring exercises to ensure Conformity to standards by developers | Metro Wide |  |  |  |  |  | 3,000 |  |  |  |  | Works | SPC |  |  |
| 3. Infrastructure Delivery and Management | SP3.2 Public Works, Rural Housing & Water Mangt | Procure working tools (Schmidt hammer, Wheel measuring roller) for effective supervision | Metro Wide |  |  |  |  |  |  | 50,000 |  |  |  | Works |  |  |  |
| 3. Infrastructure Delivery and Management | SP2.3 Physical & Spatial Planning Development | Support for Donor funded projects | Metro Wide |  |  |  |  |  |  | 100,000 |  |  |  | Planning Unit | HODs |  |  |
| 3. Infrastructure Delivery and Management | SP3.3 Urban Roads Management | Supply of Street lights in the Kumasi Metropolis | Metro Wide |  |  |  |  |  | 500,000 | 1,5000 |  |  |  | Works | Assembly Members |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities | Location |  | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| 3. Infrastructure Delivery and Management | SP3.3 Urban Roads Management | Construct 5No. Metal footbridges | Atasomanso Moshie Zongo Duase/Ohwim Amankwatia |  |  |  |  |  |  | 500,000 |  |  |  | Metro Roads | Assembly Members |  |  |
| 3. Infrastructure Delivery and Management | SP3.3 Urban Roads Management | Maintenance of Metal Footbridges | Metro Wide |  |  |  |  |  |  | 150,000 |  |  |  | Metro Roads | Assembly Members |  |  |
| 3. Infrastructure Delivery and | SP3.3 Urban Roads Management | Construct Drains in 3No. areas and improve box culvert and access roads | Abrepo Junc. Krofrom E FNT/ Truba |  |  |  |  |  |  | 1,000,000 |  |  |  | Metro Roads | Assembly Members |  |  |
| 3. Infrastructure Delivery and | SP3.3 Urban Roads Management | Install Pedestrian Guardrails and replace metal gratings and slaps | GRA Area KATH |  |  |  |  |  |  | 100,000 |  |  |  | Metro Roads | Assembly Members |  |  |
| 3. Infrastructure Delivery and Management | SP3.3 Urban Roads Management | Maintenance of Green area and Grasscutting works at the medians | Suame R/A-Sofoline; Ahmadiya R/A-Asafo Neoplan; Ahmadiya R/A-Consar, Nhyiaeso, Ridge & Danyame areas |  |  |  |  |  |  | 100,000 |  |  |  |  |  |  |  |
| 3. Infrastructure Delivery and Management | SP3.3 Urban Roads Management | Regrading of selected roads in the Kumasi Metropolis | Metro Wide |  |  |  |  |  |  | 200,000 |  |  |  | Metro Roads | Hon. Assembly Members |  |  |
| 3. Infrastructure Delivery and Management | SP3.4 Transport & Traffic Management | Carry out operational activities to improve upon public transport services &urban mobility | Metro Wide |  |  |  |  |  | 5,000 |  |  |  |  | Transport Dept. | MTTD |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities | Location |  | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| 3. Infrastructure Delivery and Management | SP3.4 Transport & Traffic Management | Implement the AFD sponsored ASToN and MYC projects | Metro Wide |  |  |  |  |  |  | 15,000 |  |  |  | Transport Dept. |  |  |  |
| 3. Infrastructure Delivery and Management | SP3.4 Transport & Traffic Management | Implement the partnership for Healthy Cities and Road Safety project/ BIGRS | Metro Wide |  |  |  |  |  |  | 50,000 |  |  |  | Transport Dept. |  |  |  |
| 4. Economic Development | SP1.1 General Administration | Procure Office Supplies including computers, Laptops, Furniture, etc | Metro Wide |  |  |  |  |  |  | 100,000 |  |  |  | IT Unit | Beneficiaries |  |  |
| 5. Environmental n Sanitation Management | SP5.2 Natural Resources Conservation | Plant and Nurture to growth 5,000 trees in schools, communities and along major routes | Metro Wide |  |  |  |  |  |  | 5000 |  |  |  | Forestry | Environmental Health Unit |  |  |
| 5. Environmental n Sanitation Management | SP5.2 Natural Resources Conservation | Implement Bloomberg sponsored Youth Climate Action project | Metro wide |  |  |  |  |  |  |  | 800,000 |  |  | MPCU |  |  |  |
| 5. Environmental n Sanitation Management | SP5.2 Natural Resources Conservation | Organize sensitization exercises in communities on the need to plant more trees | Metro Wide |  |  |  |  |  |  | 2000 |  |  |  | Forestry | Environmental Health Unit |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities | Location |  | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| Dimension IV: Governance, Corruption and Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.Management and Administration | SP1.1 General Administration | Organize 2no Town hall meetings annually to account community members on the implementation of Assembly programmes and activities | Prempeh Assembly Hall |  |  |  |  |  |  | 40,000 |  |  |  | Planning Unit |  | Budget & Ratings |  |
| 1.Management and Administratio | SP1.1 General Administration | Complete the construction of 2No. Sub metro Offices | Bantama Manhyia North |  |  |  |  |  | 1,000000 |  |  |  |  | Works |  | Beneficiaries |  |
| 1.Management and Admini | SP1.1 General Administration | Support for Community Initiated projects and Sub District Structures | Metro Wide |  |  |  |  |  | 500000 |  |  |  |  | Works |  | Submetros |  |
| 1.Management and Administration | SP1.1 General Administration | Organize talk shows at radio stations to explain the services provided by the Assembly & how to access them | Metro Wide |  |  |  |  |  | 5,000 |  |  |  |  | PRO |  | ISD |  |
| 1.Management and Admin | SP1.1 General Administration | Organize MCE’s electoral area tour | Metro Wide |  |  |  |  |  | 10,000 | 10,000 |  |  |  | PRO |  | ISD |  |
| 1.Management and Admin | SP1.1 General Administration | Rehabilitate Office & residential buildings | Metro Wide |  |  |  |  |  | 100,000 | 2,000,000 |  |  |  | Works |  | HODs |  |
| 1.Management and Admin | SP1.1 General Administration | Support Assembly Membestreetrs Community Engagements | Metro Wide |  |  |  |  |  |  | 400,000 |  |  |  | Assembly Members |  | Community Members |  |
| 1.Management and Administration | SP1.6 Budgeting & Rating | Train Staff of the Assembly on Performance Based Budgeting and GIFMIS | Metro Wide |  |  |  |  |  | 5000 | 5000 |  |  |  | Budget |  | Finance |  |
| 1.Management and Administratio | SP1.2 Finance & Audit | Train all staff on Local Government Service Protocols | Prempeh Assembly Hall |  |  |  |  |  | 20,000 |  |  |  |  | HR |  | Finance |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities | Location |  | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| 1.Management and Admini | SP1.2 Finance & Audit | Provide IT system to link centralized departments to the revenue unit | Metro Wide |  |  |  |  |  |  | 15,000 |  |  |  | IT |  | Finance |  |
| 1.Management and Administration | SP1.2 Finance & Audit | Organize radio programs monthly to educate tax payers about the need to pay taxes | Metro Wide |  |  |  |  |  | 5000 |  |  |  |  | Finance |  | PRO |  |
| 1.Management and Administration | SP1.6 Budgeting & Rating | Organize stakeholder engagements with the business community on Fee fixing resolution | Prempeh Assembly Hall |  |  |  |  |  | 5000 | 5000 |  |  |  | Budget |  | Finance |  |
| 1.Management and Adminion | SP1.6 Budgeting & Rating | Review Budget/Plan at Mid- year and prepare revenue improvement action plan | Metro Wide |  |  |  |  |  | 3000 |  |  |  |  | Budget |  | Finance |  |
| 1.Management and Administration | SP1.6 Budgeting & Rating | Organize Budget implementation monitoring and training at the submetros | Metro Wide |  |  |  |  |  | 5000 |  |  |  |  | Budget |  | Finance |  |
| 1.Management and Admini | SP1.7 Legal Services | Construct and furnish 1No. Police Station | Asafo |  |  |  |  |  |  |  | 1,000000 |  |  | Legal |  | Works |  |
| 1.Management and Administration | SP1.3 Human Resource | Train Assembly Members on their Roles and Responsibilities | Metro Wide |  |  |  |  |  |  | 20000,000 |  |  |  | HR |  |  |  |
| 1.Management and Adminis | SP1.3 Human Resource | Train staff on Data Collection and Management & implement Smart Cities Project | Metro Wide |  |  |  |  |  |  | 50,000 |  |  |  | HR |  |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities | Location |  | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| 1.Management and Admin | SP1.4 Planning Coordination & Statistics | Disseminate & organize stakeholder engagement on the 2021 Census and organize data collection on hotspots for drug peddlers especially the youth | Metro Wide |  |  |  |  |  |  | 15,000 |  |  |  | Statistics |  | PRO |  |
| 1.Management and Admin | SP1.4 Planning Coordination & Statistics | Train MPCU Members on use of Stats Bank and best practices for quality data | Metro Wide |  |  |  |  |  | 10,000 |  |  |  |  | Statistics |  |  |  |
| 1.Management and Administratio | SP1.6 Budgeting & Rating | Gazette and Distribute 2025 Fee Fixing Resolution | Metro Wide |  |  |  |  |  | 25,000 |  |  |  |  | Budget |  | Finance |  |
| Development Dimension V: Emergency planning and response (including covid-19 recovery plan) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Environment and Sanitation | SP5.1 Disaster Devt and Mangt | Organize educational campaigns on fire and floods for all fuel stations | Metro Wide |  |  |  |  |  | 2500 | 3000 |  |  |  | NADMO |  | Fire Service/ WMD |  |
| 5. Environment and Sanitatio | SP5.1 Disaster Devt and Mangt | Carryout inspection and evaluation of facilities to ensure safety | Metro Wide |  |  |  |  |  | 3000 |  |  |  |  | NADMO |  | Works |  |
| 5. Environment and Sanitation | SP5.1 Disaster Devt and Mangt | Desilt chocked drains and streams | Metro Wide |  |  |  |  |  | 500000 |  |  |  |  | NADMO |  | Works/Urban Roads |  |
| 5. Environment and Sanitation | SP5.1 Disaster Devt and Managt | Build the Capacity of NADMO Staff in disaster management | Metro Wide |  |  |  |  |  | 4,000 |  |  |  |  | NADMO |  | HR |  |
| 5. Environment and Sanitation | SP5.1 Disaster Devt and Mangt | Organize celebration of World Disaster Day | Metro Wide |  |  |  |  |  |  | 4000 |  |  |  | NADMO |  |  |  |
| 1. Management and Administ | SP1.4 Planning, Coordination & Statistics | Train Assembly staff on Communication skills | Metro Wide |  |  |  |  |  |  | 30,000 |  |  |  | HR |  |  |  |
| Programme (PBB) | Sub-Programme (PBB) | Activities | Location |  | 2025 |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |  |  |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | IGF | GOG | Others | New | Ongoing | Lead | Collaborating |  |  |
| 1. Management and Administration | SP1.4 Planning, Coordination & Statistics | Prepare 2025 Annual Action Plan and Composite Budget and 2026 – 2029 MTDP | Metro Wide |  |  |  |  |  |  | 270,000 |  |  |  | MPCU |  |  |  |
| 1. Management and Administratio | SP1.4 Planning, Coordination & Statistics | Conduct routine monitoring of Assembly’s on-going projects and programs | Metro Wide |  |  |  |  |  |  | 40,000 |  |  |  | MPCU |  |  |  |
| Development Dimension VI: Implementation, coordination, monitoring and evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Management and Administration | SP1.4 Planning, Coordination & Statistics | Organise quarterly MPCU/Budget Committee meetings | Metro Wide |  |  |  |  |  |  | 30,000 |  |  |  | MPCU |  |  |  |
| 1. Management and Administration | SP1.4 Planning, Coordination & Statistics | Organize participatory M&E on assembly activities | Metro Wide |  |  |  |  |  |  | 70,000 |  |  |  | MPCU |  |  |  |